## Sheet1
Week # | Main Task | Sub-task | Task Owner | Deadline | Est. Time | Actual Time | Status | Comments
Week 5 - Skeleton | 1. Game Page | Sketch game page structure | Michael LaPlante | 2014-02-05 | 30 min | 20 min | Done
2/1/2014 - 2/8/2014 |  | Create skeleton layout | Michael LaPlante | 2014-02-05 | 2 hours | 1 hour 30 min | Done | Create basic structure, add links
|  | Make it pretty | Michael LaPlante | 2014-02-05 | 2 hours | 2 hours 30 min | Done | Add dummy text & images, refine layout
| 2. User Profile Page | Sketch user profile page structure | Chuqi Qiu | 2014-02-05 | 20 min | 30 min | Done
|  | Add login with Facebook/Social Media | Chuqi Qiu | 2014-02-05 | 20 min
|  | Create User Profile Page | Chuqi Qiu | 2014-02-05 | 1 hour | 2 hours | Done
|  | Add User Settings Page | Chuqi Qiu | 2014-02-05 | 1 hour | 2 hours
| 3. Home Page | Change Featured Games to grid | Ian Gilmore | 2014-02-05 | 30 min | 20 min | Done
|  | Add content to footer | Ian Gilmore | 2014-02-05 | 1 hour |  | Done
| 4. Create Website Skeleton | Add links to dummy pages | David Williams | 2014-02-05 | 30 min | 1 hour | Done
|  | Create Review Page (dummy) | David Williams | 2014-02-05 | 1 hour | 20 min | Done
|  | Account and Setting Page | David Williams | 2014-02-05 | 1 hour | 20 min | Done
|  | Additional Dummy Pages | David WIlliams | 2014-02-05 | 1.5 hours | 1hour | Done
|  | Sketch Navigational Skeleton | Ian Gilmore | 2014-02-05 | 1 hour | 30 min | Done | Link
|  | Create Individual Header/Footer html files | Michael LaPlante | 2014-02-05 | 45 min
| 5. R&D | Research Feed Implementation | Ian Gilmore | 2014-02-08 | 1 hour
|  | Research Angular JS | Ian Gilmore | 2014-02-08 | 1 hour
|  | Review Page Cover Image Research | Chuqi Qiu | 2014-02-08 | 1 hour
Week 6 - Meat on Bones
2/9/2015 - 2/16/2015 | Create/Edit Review Page | Add cover image section on the top | Michael LaPlante | 2014-02-12 | 1 hour
|  | Text Fields | Michael LaPlante | 2014-02-12 | 1 hour
|  | Game Search Section | Michael LaPlante | 2014-02-12 | 1 hour
|  | Publish/Cancel btns | Chuqi Qiu | 2014-02-12 | 1 hour
| Published Review Page | Edit/Delete btns | Chuqi Qiu | 2014-02-12 | 45 min
|  | Delete Review Dialogue Box | Chuqi Qiu | 2014-02-12 | 45 min
| Search Page | Tagging System | Ian Gilmore | 2014-02-14 | 20 min
|  | Dummy Reviewers/Games | Ian Gilmore | 2014-02-14 | 20 min
| Log-in/Create Account | Log-in links | Ian Gilmore | 2014-02-14 | 35 min
|  | Create Separate Header and Footer Files using Bootstrap.js | David WIlliams | 2014-02-14 | 35 min
|  | Create "About Page" | David WIlliams | 2014-02-14 | 50 min
| R&D | Back-end Server | David WIlliams | 2014-02-14 | 30 min
|  | Research Search Backend | David WIlliams | 2014-02-14 | 30 min
Week 7 - Ready for Testing
2/17/15 - 2/24/15 | Check all the naviagtion flows | Invite both professionals and unfamiliar users | Michael LaPlante | 2015-02-22 | 1 hour
|  | Collect feedbacks from users | Michael LaPlante | 2015-02-22 | 30 min
|  | Make changes accordingly | Chuqi Qiu | 2015-02-22 | 45 min
|  | Create a report based on the feedback for reference | Chuqi Qiu | 2015-02-22 | 1 hour
| Back-End Support for Users | Store users tokens | Ian Gilmore | 2015-02-22 | 1 hour 30 min
|  | Server maintanence plan | Ian Gilmore | 2015-02-22 | 20 min
|  | Error and wrong invalid input prevention | David Wiiliams | 2015-02-22 | 1 hour
|  | User password reset | David Wiiliams | 2015-02-22 | 1 hour
Week 8 - Test your Prototype
2/24/2015 - 3/2/2015
Week 9 - Results!
3/3/2015 - 3/10/2015
Week 10 - Final Presentation
3/10/2015 - 3/17/2015 | Prepare presentation and create a timeline for the entire designing process. Make presentation slides accordingly. Finalize the project and test thoroughly.